## Sheet1
ID | Actual Start | Actual Finish | Status | % Complete | Runsheet ID | Notes | Task Name | Start | Finish | Duration | Resource Names | Predecessors | FDR1 Record Count | FDR2 Record Count | FDR2 Durations | Not Started
1 |  |  | In Progress | 20% |  |  | Portal | Tue 11/01/22 4:00 PM | Wed 9/03/22 6:45 AM | 1358.75 hrs | [5 empty] | In Progress
2 |  |  | In Progress | 51% |  |  | CE Portal Set-up | Thu 3/02/22 9:00 AM | Sat 5/02/22 3:00 PM | 54 hrs? | [5 empty] | Complete
3 |  |  | In Progress | 100% |  |  | 1.0 Prerequisite Requirements | Thu 3/02/22 9:00 AM | Thu 3/02/22 1:30 PM | 4.5 hrs | [5 empty] | Delayed
4 | 11:10:00 AM Wed | 5:00 PM Mon | Complete | 100% | P1.11 | Need to escalate via Rob Taranto and Craig Gorman | Request certificates for friendly URL Portal name conversion | Tue 11/01/22 4:00 PM | Tue 11/01/22 4:30 PM | 0.5 hrs | Craig James |  |  |  |  | Behind Schedule
5 | 11:35 | 11:50 | Complete | 100% | P1.1 | portal-bslau.crm6dynamics.com | Access to a global administrator to create CE Environment | Mon 31/01/22 9:00 AM | Mon 31/01/22 9:30 AM | 0.5 hrs | Simaranjit Singh Bhalla |  |  |  |  | Blocked
6 | 11:14 | 11:20 | Complete | 100% | P1.1.5 |  | Set-up Prod Sharepoint for Pricelist folders | Wed 2/02/22 9:00 AM | Wed 2/02/22 9:30 AM | 0.5 hrs | Craig Gorman
7 | 11:25 | 13:50 | Complete | 100% | P1.1.6 |  | Set-up Blob container for Production | Wed 2/02/22 9:00 AM | Wed 2/02/22 9:30 AM | 0.5 hrs
8 | 14:00 | 15:15 | Complete | 100% | P1.8 |  | Ensure blob sites configuration | Wed 2/02/22 1:30 PM | Wed 2/02/22 3:30 PM | 2 hrs | Craig James | 7FS+4 hrs
9 | 14:00 | 17:40 | Complete | 100% | P1.9 | May need to check subscriptions for Production environment | Ensure access to Azure Subscription for configuration of blob storage and key vault (service accts & users) | Wed 2/02/22 3:30 PM | Wed 2/02/22 7:30 PM | 4 hrs | Craig Gorman | 8
10 | 12:30 | 13:55 | Complete | 100% | P1.10 |  | Ensure Azure Apps Registration - CE graph API and keyvault | Wed 2/02/22 9:00 AM | Wed 2/02/22 9:30 AM | 0.5 hrs | Craig Gorman
11 | 12:30 | 14:00 | Complete | 100% | P1.7 |  | Availability of 'Do not reply' mailbox | Wed 2/02/22 9:00 AM | Wed 2/02/22 9:30 AM | 0.5 hrs | Craig Gorman
12 | 16:57 | 17:54 | Complete | 100% | P1.2 |  | Ensure Sharepoint set-up correctly - folders for Pricelists. | Wed 2/02/22 3:30 PM | Wed 2/02/22 4:00 PM | 0.5 hrs | Craig James | 6
13 | 17:53 | 17:54 | Complete | 100% | P1.3 | Need to add people individually? Done by CJ | Ensure Sharepoint access for BSLAU - D365 CE CIPA members | Wed 2/02/22 7:30 PM | Wed 2/02/22 8:00 PM | 0.5 hrs | Craig James | 10
14 | 14:55 | 21:20 | Complete | 100% | P1.4 | MCS task & prerequisite | Configuration of application/ system users for integration | Wed 2/02/22 3:30 PM | Wed 2/02/22 4:00 PM | 0.5 hrs | Ashok Singh | 12
15 | 14:55 | 18:45 | Complete | 100% | P1.5 | MCS task & prerequisite | Configuration of application/ system users in CE and Fin Ops | Wed 2/02/22 4:00 PM | Wed 2/02/22 4:30 PM | 0.5 hrs | Ashok Singh | 15
16 | 18:00 | 20:24 | Complete | 100% | P1.5.5 | New 01/02/22 | Create a pipeline for deploying solutions to production. | Wed 2/02/22 4:30 PM | Wed 2/02/22 8:30 PM | 4 hrs | Ashok Singh | 16
17 | 13:00 | 12:00 | Complete | 100% | P3.19 | Nick is on leave - keeno.gonzales@dxc.com | Provide Power BI URL to Microsoft | Wed 2/02/22 9:00 AM | Wed 2/02/22 9:30 AM | 0.5 hrs | Nick Maung
18 |  |  | Complete | 100% |  |  | 2.0 Installation Activities | Wed 2/02/22 9:30 AM | Thu 3/02/22 8:10 PM | 34.67 hrs
19 | 18:23 | 20:22 | Complete | 100% | P2.1 | Must follow P1.9 | Configuration of Key vault, Blob Storage in Power automate environment variables | Wed 2/02/22 7:30 PM | Wed 2/02/22 8:30 PM | 1 hr | Ashok Singh | 9
20 | 18:25 | 18:45 | Complete | 100% | P2.2 |  | Set-up the required apps in production CE | Wed 2/02/22 3:30 PM | Wed 2/02/22 4:30 PM | 1 hr | Simaranjit Singh Bhalla
21 | 19:22 | 16:22 | Complete | 100% | P2.4 | Required prior to MDM, can take up to 24hrs from MS support | Request for server scale up | Wed 2/02/22 4:30 PM | Thu 3/02/22 4:30 PM | 24 hrs | Simaranjit Singh Bhalla | 20
22 | 13:56 | 14:25 | Complete | 100% | P2.5 |  | Setup Dual Write App | Thu 3/02/22 1:30 PM | Thu 3/02/22 2:30 PM | 1 hr | Ashok Singh
23 | 14:00 | 14:14 | Complete | 100% | P2.6 |  | Setup of Customer Self Service Portal | Thu 3/02/22 2:30 PM | Thu 3/02/22 3:30 PM | 1 hr | Ashok Singh | 22
24 | 8:00 | 10:30 | Complete | 100% | P2.6.5 | Must follow task P1.11. New 01/02/22. URL updated to www.bluescopeconnect.com.au | Upload whitelisting certificates for the portal. | Thu 3/02/22 3:30 PM | Thu 3/02/22 4:00 PM | 0.5 hrs | Ashok Singh | 23,4 | not impacting Thursday's activities
25 | 15:00 | 17:45 | Complete | 100% | P2.7 |  | Running of dev ops pipeline for installation of solutions. | Thu 3/02/22 4:00 PM | Thu 3/02/22 6:00 PM | 2 hrs | Ashok Singh
26 | 14:00 | 14:30 | Complete | 100% | P2.8 | pre-req = P1.7 | Setup of Mail Box (Do not reply) | Thu 3/02/22 6:00 PM | Thu 3/02/22 7:00 PM | 1 hr | Ashok Singh | 11
27 | 14:35 | 14:55 | Complete | 100% | P2.8.5 | New 01/02/22 | Disable email tracking in system settings | Thu 3/02/22 7:00 PM | Thu 3/02/22 7:05 PM | 5 mins | Ashok Singh
28 | 17:50 | 19:00 | Complete | 100% | P2.9 |  | Setup of Sharepoint Integration | Thu 3/02/22 7:05 PM | Thu 3/02/22 8:05 PM | 1 hr | Ashok Singh | 25
29 | 19:15 | 21:55 | Complete | 100% | P2.10 |  | Migrate Portal Configurations | Thu 3/02/22 8:05 PM | Thu 3/02/22 10:05 PM | 2 hrs | Ashok Singh | 25
30 | 21:55 | 22:05 | Complete | 100% | P2.10.6 | New 01/02/22 | Setup teams in CE and provide them the relevant security roles. | Thu 3/02/22 10:05 PM | Thu 3/02/22 10:10 PM | 5 mins | Ashok Singh | 29
31 | 13:56 | 15:15 | Complete | 100% | P2.11 | Issue thru to 2.14 as a group | Ensure all flows and workflows are activated and assigned to service account users / connectors | Thu 3/02/22 10:10 PM | Thu 3/02/22 11:10 PM | 1 hr | Ashok Singh | 25
32 | 15:30 | 16:30 | Complete | 100% | P2.11.5 | New 01/02/22. CG in progress to set-up UAT connection in addition to PROD | Update Run as user for the flows as per the setup guide. | Thu 3/02/22 11:10 PM | Thu 3/02/22 11:15 PM | 5 mins | Ashok Singh | 25
33 | 22:45 | 23:40 | Complete | 100% | P2.12 |  | Modify Environment variables as per the latest details | Thu 3/02/22 11:15 PM | Fri 4/02/22 12:15 AM | 1 hr | Ashok Singh | 25
34 | 23:15 | 23:20 | Complete | 100% | P2.13 | Changed by SIM 01/02/22 | Change Site settings and settings in Portal Configurations and Change PortalURL content snippet in production | Fri 4/02/22 12:15 AM | Fri 4/02/22 12:20 AM | 5 mins | Ashok Singh | 29
35 | 0:10 | 0:15 | Complete | 100% | P2.13.6 | New 01/02/22 | Update System settings concering language, currency etc. (Refer to Deployment Guide) | Fri 4/02/22 12:20 AM | Fri 4/02/22 12:25 AM | 5 mins | Ashok Singh
36 | 0:17 | 0:23 | Complete | 100% | P2.14 | New 01/02/22 - last task to issue for 3/2 | Update System Configuration Welcome email in production | Fri 4/02/22 12:25 AM | Fri 4/02/22 12:30 AM | 5 mins | Ashok Singh | 25
37 |  |  | In Progress | 90% |  |  | 3.0 Remaining Set-up Activities | Thu 3/02/22 9:00 AM | Thu 24/02/22 4:00 PM | 511 hrs
38 | NA | NA | Complete | 100% | P3.14 | link to Master runsheet -check with Mark when D365 will be ready to connect with CE | Provision D365 environment | Thu 3/02/22 9:00 AM | Thu 3/02/22 1:00 PM | 4 hrs | Adam Cheeseman
39 | 14:00 | 15:00 | Complete | 100% | P3.18 | Needs to follow Smartsend set-up in F&O. Waiting on access to F&O following confi set-up | Ensure Smartsend setting for Blob from F&O are configured in Smartsend correctly | Fri 4/02/22 4:00 PM | Mon 7/02/22 10:00 AM | 1 hr | Craig James
40 | 13:55 | 14:10 | Complete | 100% | P3.2 | Intersects with Environment runsheet | Ensure correct blob container(/d365-fotoportalpdf) map in "SmartSend - Process documents stored in Blob storage" flow | Fri 4/02/22 1:30 PM | Fri 4/02/22 2:00 PM | 0.5 hrs | Ashok Singh | 19,35
41 | 14:20 | 14:55 | Complete | 100% | P3.4 |  | Ensure that plugin (Microsoft.Dynamics.SCMExtended.Plugins.OrderNumberAssignment: Create of salesorder) excution order set '2' | Fri 4/02/22 2:00 PM | Fri 4/02/22 2:30 PM | 0.5 hrs | Ashok Singh | 40
42 | 14:55 | 15:20 | Complete | 100% | P3.5 |  | Validate Sales Order sequence should be configured correctly | Fri 4/02/22 2:30 PM | Fri 4/02/22 3:00 PM | 0.5 hrs | Ashok Singh | 41
43 | 15:20 | 15:35 | Complete | 100% | P3.3 |  | Assign Power BI URL to Power Portal Stocksaver link | Fri 4/02/22 3:00 PM | Fri 4/02/22 4:00 PM | 1 hr | Ashok Singh | 12,38
44 | 16:00 | 16:17 | Complete | 100% | P3.15 | Intersects with Environment runsheet - start Monday pm? | Set-up dual write between Portal CE and FinOps environment | Fri 4/02/22 2:30 PM | Fri 4/02/22 2:45 PM | 15 mins | Ishita Singhal | 22
45 | 16:20 | 16:35 | Complete | 100% | P3.16 |  | Virtual Entity Setup in FinOps | Fri 4/02/22 2:45 PM | Fri 4/02/22 3:00 PM | 15 mins | Ishita Singhal | 45
57 | 15:00 |  | Complete | 100% | P9.1 | Done - Extended for another 12 months, however will need an action for DXC team to again extend password change in 12 mths time. Refer Tech Debt #130347 | Ensure svc-d365ce-admin is set to "non expiry" | Mon 7/02/22 8:00 AM | Mon 7/02/22 8:30 AM | 0.5 hrs | Craig Gorman | 36
51 | 16:25 | 17:55 | Complete | 100% | P3.17 | will issue 7/2 rather than 8/2. More like a 1 hr task | Virtual Entity Setup in CE | Tue 8/02/22 1:30 PM | Tue 8/02/22 1:45 PM | 15 mins | Ashok Singh | 38
52 | NA | NA | Complete | 90% | P3.17.5 | BSME confirmed lay-out of, calling complete and changes will be moved from Dev to Prod. Once this done by Sim, we will mark as complete. Remaining URL link will be provided ~22nd Feb and uploaded then as agreed. | Deploy the User Guides page into Production | Mon 7/02/22 2:00 PM | Wed 9/02/22 3:00 PM | 1 hr | Ashok Singh
| 15:00 | 16:30 | Complete | 100% | P3.17.6 | Bug took priority for Ashok's time during 9/2 | Smoke test the Power automate flows | Wed 9/02/22 3:00 PM | Wed 9/02/22 7:00 PM | 4 hrs | Ashok Singh
46 |  |  | Not Started | 0% | P3.6 | Ross Mireylees to provide Steelconnect User list to CJ | Extract from Steelconnect: User list | Thu 17/02/22 9:00 AM | Thu 17/02/22 11:00 AM | 2 hrs | Ross Mireylees
47 |  |  | Not Started | 0% | P3.7 | Needs to be documented. Improve the task list and ensure the right people are listed | Transform Steelconnect user list for upload to CE: Users to Roles and Customers | Thu 17/02/22 11:00 AM | Thu 17/02/22 1:00 PM | 2 hrs | Craig James | 47
48 |  |  | Not Started | 0% | P3.9 | Needs to be documented. Require template | Extract from Steelconnect; Price List list, Customer Technical Data Sheet list | Thu 17/02/22 11:00 AM | Thu 17/02/22 12:00 PM | 1 hr | Ross Mireylees | 48
49 |  |  | Not Started | 0% | P3.10 | Needs to be documented. Require template | Transform Steelconnect Price list and Customer Technical Data Sheet list for upload to CE | Thu 17/02/22 1:00 PM | Thu 17/02/22 3:00 PM | 2 hrs | Craig James | 49
50 | NA | NA | Complete | 100% | P3.11 | Needs to be documented - CJ already has the list (so done) | Extract from Steelconnect: Delivery Week Calendars | Thu 17/02/22 12:00 PM | Thu 17/02/22 1:00 PM | 1 hr | Ross Mireylees | 49
53 |  | 10 min | Complete | 100% | P3.20 | Complete - Done via FDR2. AC to check with Craig Gorman if there are any plans re: the VM | Availability of VM for running packages | Thu 24/02/22 2:00 PM | Thu 24/02/22 2:30 PM | 0.5 hrs | Ashok Singh
54 |  | 10 min | Complete | 100% | P3.21 | Complete - done during FDR2 | Installation of Kingswaysoft connector | Thu 24/02/22 2:30 PM | Thu 24/02/22 3:00 PM | 0.5 hrs | Ashok Singh | 54
55 |  | 30 min | Complete | 100% | P3.22 | Complete - dine via FDR2 | Installation of Scripts / packages / jobs for DM | Thu 24/02/22 3:00 PM | Thu 24/02/22 3:30 PM | 0.5 hrs | Ashok Singh | 55
56 |  |  | Not Started | 0% | P3.23 |  | Set up connections for both Dynamics CE and FinOps | Thu 24/02/22 3:30 PM | Thu 24/02/22 4:00 PM | 0.5 hrs | Ashok Singh | 56
58 |  |  | Not Started | 0% |  |  | 4.0 Prep for Master Data Synch | Sun 27/02/22 7:30 AM | Wed 2/03/22 7:00 PM | 83.5 hrs
59 |  |  | Not Started | 0% | P4.1 |  | D365 PVT | Sun 27/02/22 7:30 AM | Wed 2/03/22 1:30 PM | 78 hrs
60 |  |  | Not Started | 0% | P4.2 | Mark W has a task to refresh the entity list after the restore | Restore D365 Database | Wed 2/03/22 1:30 PM | Wed 2/03/22 6:30 PM | 5 hrs |  | 59 | MW confirmed refresh
61 |  |  | Not Started | 0% | P4.3 |  | Advises Portal synch may occur | Wed 2/03/22 6:30 PM | Wed 2/03/22 7:00 PM | 30 mins | Adam Allen | 60
62 |  |  | Not Started | 0% | P4.4 |  | Communicate to Program in particular Data Migration, that NO further changes to Product / Customers / CPN are to occur | Wed 2/03/22 7:00 PM | Wed 2/03/22 7:00 PM | 0 hrs | Adam Cheeseman | 61
64 |  |  | Not Started | 0% | P10.4 |  | Remove restriction - take Portal out of maintenance mode | Wed 2/03/22 7:00 PM | Wed 2/03/22 7:03 PM | 3 mins | Ashok Singh
65 |  |  | Not Started | 0% |  |  | 5.0 CE Master Data Synch | Wed 2/03/22 7:00 PM | Thu 3/03/22 1:40 AM | 6.67 hrs
66 |  |  | Not Started | 0% | P3.24 |  | Validate Change Tracking is on for all Entities that will use DW | Wed 2/03/22 7:00 PM | Wed 2/03/22 8:00 PM | 1 hr | Ishita Singhal | 58,63
67 |  |  | Not Started | 0% | P5.1 | Needs to be documented (Ishita) | Set-up Advance Find and Import parameters | Wed 2/03/22 8:00 PM | Wed 2/03/22 9:00 PM | 1 hr | Ashok Singh | 66 |  |  | 1.10 hrs
68 |  |  | Not Started | 0% | P5.2 | split this into Master and Transactional data | Prepare the SSIS files - extract Products, Global Products , CPN Headers and Specifications | Wed 2/03/22 9:00 PM | Wed 2/03/22 9:20 PM | 20 mins | Ishita Singhal | 67 |  |  | 33 min
69 |  |  | Not Started | 0% | P5.5 |  | Synch Data Entity line 1 - Legal Entities | Wed 2/03/22 9:20 PM | Wed 2/03/22 9:25 PM | 5 mins | Ishita Singhal | 68 | 1010-3 | 1010 - 3 | 18 min
70 |  |  | Not Started | 0% | P5.6 |  | Synch Data Entity line 2 - Sites | Wed 2/03/22 9:25 PM | Wed 2/03/22 9:31 PM | 6 mins | Ishita Singhal | 69 | 1010-3 1310-16 | 1010-3 1310-16 | 2 min
71 |  |  | Not Started | 0% | P5.7 |  | Synch Data Entity line 3 - Currencies | Wed 2/03/22 9:31 PM | Wed 2/03/22 9:36 PM | 5 mins | Ishita Singhal | 70 | 1010-177 | 1010 - 177 | 5 min
72 |  |  | Not Started | 0% | P5.8 |  | Synch Data Entity line 4 - Customer Groups | Wed 2/03/22 8:30 PM | Wed 2/03/22 8:35 PM | 5 mins | Ishita Singhal | 64 | 1010-10 1310-10 | 1010 - 10 1310 - 10 | 3 min
73 |  |  | Not Started | 0% | P5.9 |  | Synch Data Entity line 5 - Units | Wed 2/03/22 8:35 PM | Wed 2/03/22 8:40 PM | 5 mins | Ishita Singhal | 72 | 1010-55 | 1010 - 55 | 3 mins
74 |  |  | Not Started | 0% | P5.10 |  | Synch Data Entity line 6 - Widths | Wed 2/03/22 8:40 PM | Wed 2/03/22 8:45 PM | 5 mins | Ishita Singhal | 73 | 1010-1273 | 1010 - 1286 | 7 mins
75 |  |  | Not Started | 0% | P5.11 |  | Synch Data Entity line 7 - Lengths | Wed 2/03/22 8:45 PM | Wed 2/03/22 8:49 PM | 4 mins | Ishita Singhal | 74 | 1010-929 | 1010 - 944 | 6 mins
76 |  |  | Not Started | 0% | P5.12 |  | Synch Data Entity line 8 - Styles | Wed 2/03/22 8:49 PM | Wed 2/03/22 8:54 PM | 5 mins | Ishita Singhal | 75 | 1010-513 | 1010 - 520 | 5 mins
77 |  |  | Not Started | 0% | P5.13 |  | Synch Data Entity line 9 - Configurations | Wed 2/03/22 8:54 PM | Wed 2/03/22 8:59 PM | 5 mins | Ishita Singhal | 76 | 1010-1 | 1010 - 1 | 2 mins
78 |  |  | Not Started | 0% | P5.16 |  | Synch Data Entity line 10 - Payment dats CDS | Wed 2/03/22 8:59 PM | Wed 2/03/22 9:04 PM | 5 mins | Ishita Singhal | 77 | 1010-6 1310-6 | 1010 - 6 1310 - 6 | 1 mins
79 |  |  | Not Started | 0% | P5.17 |  | Synch Data Entity line 11 - Payment Schedule | Wed 2/03/22 9:04 PM | Wed 2/03/22 9:09 PM | 5 mins | Ishita Singhal | 78 | 1010-0 1310-0 | 1010-0 1310-0 | 2 mins
80 |  |  | Not Started | 0% | P5.18 |  | Synch Data Entity line 12 - Product dimension groups | Wed 2/03/22 9:09 PM | Wed 2/03/22 9:14 PM | 5 mins | Ishita Singhal | 79 | 1010-5 1310-0 | 1010-5 1310-0 | 3 mins
81 |  |  | Not Started | 0% | P5.19 |  | Synch Data Entity line 13 - All Products | Wed 2/03/22 9:14 PM | Wed 2/03/22 9:19 PM | 5 mins | Simaranjit Singh Bhalla | 80 | 1010-35024 1310-0 | 1010 - 35971 | 2 mins
82 |  |  | Not Started | 0% | P5.20 |  | Synch Data Entity line 14 - CDS released distinct products - 1010 | Wed 2/03/22 9:19 PM | Wed 2/03/22 9:34 PM | 15 mins | Simaranjit Singh Bhalla | 81 | 1010-17750 | 1010 - 18090 | 10 mins
83 |  |  | Not Started | 0% | P5.20 |  | Synch Data Entity line 14 - CDS released distinct products - 1310 | Wed 2/03/22 9:34 PM | Wed 2/03/22 9:49 PM | 15 mins | Simaranjit Singh Bhalla | 82 | 1310-10538 | 1310 - 11000 | 10 mins
84 |  |  | Not Started | 0% | P5.21 |  | Synch Data Entity line 15 - Customers V3 | Wed 2/03/22 9:49 PM | Wed 2/03/22 9:59 PM | 10 mins | Ishita Singhal | 83 | 1010-456 1310-563 |  | 10 mins
85 |  |  | Not Started | 0% | P5.22 |  | Data Load: Import Price List & customer technical data sheets lists structures | Wed 2/03/22 10:19 PM | Wed 2/03/22 11:19 PM | 1 hr | Ashok Singh | 85 |  |  | 13 mins
86 |  |  | Not Started | 0% | P5.23 |  | Validate Price list in Portal CE | Thu 3/03/22 12:25 AM | Thu 3/03/22 12:40 AM | 15 mins | Ashok Singh | 86 |  |  | 12 mins
87 |  |  | Not Started | 0% | P5.24 |  | Import Portal User into CE | Thu 3/03/22 12:40 AM | Thu 3/03/22 1:06 AM | 0.43 hrs | Ashok Singh | 87 |  |  | 5 min
88 |  |  | Not Started | 0% | P5.25 |  | Synch Data Entity line 24 - MCS customer contacts | Thu 3/03/22 1:06 AM | Thu 3/03/22 1:36 AM | 0.5 hrs | Ishita Singhal | 88 | 1010-51646 1310-0 | 1010 - 17851 | 52 min
89 |  |  | Not Started | 0% | P5.26 | as per bug 121416 - need to check the logs to make sure the accounts have loaded even though there is a warning | Confirm the child account has loaded where related to a parent | Wed 2/03/22 9:59 PM | Wed 2/03/22 10:19 PM | 20 mins | Ishita Singhal | 84 |  |  | 22 min
90 |  |  | Not Started | 0% | P5.27 | P5.26 and P5.27 can start directly after P5.21 | Synch Data Entity line 16 - Responsibilities | Wed 2/03/22 10:19 PM | Wed 2/03/22 10:34 PM | 15 mins | Ishita Singhal | 85 | 1010-361 1310-725 | 1010 - 346 1310 - 698 | 12 mins
91 |  |  | Not Started | 0% | P5.28 |  | Synch Data Entity line 17 - CDS Customer contacts | Wed 2/03/22 10:34 PM | Wed 2/03/22 10:54 PM | 20 mins | Ishita Singhal | 90 | 1010-3063 1310-0 | 1010 - 6564 | 10 mins
92 |  |  | Not Started | 0% | P5.29 |  | Synch Data Entity line 18 - Customer delivery addresses | Wed 2/03/22 10:54 PM | Wed 2/03/22 11:19 PM | 25 mins | Ishita Singhal | 91 | 1010-1397 1310-1886 | 1010 - 1406 1310 - 1891 | 13 mins
93 |  |  | Not Started | 0% | P5.29.5 |  | Synch Data Entity line 18 - Warehouse delivery addresses | Thu 3/03/22 12:25 AM | Thu 3/03/22 12:55 AM | 30 mins | Ishita Singhal | 92 |  |  | 22 min
94 |  |  | Not Started | 0% | P5.30 |  | Synch Data Entity line 19 - CDS Customer address contacts | Thu 3/03/22 12:55 AM | Thu 3/03/22 1:05 AM | 10 mins | Ishita Singhal | 93 | 1010-1649 1310-0 | 1010 - 1650 | 15 min
95 |  |  | Not Started | 0% | P5.31 |  | Synch Data Entity line 20 - Case detail | Thu 3/03/22 1:05 AM | Thu 3/03/22 1:10 AM | 5 mins | Ishita Singhal | 94 | 1010-0 1310-0 | 1010-0 1310-0 | 2 min
96 |  |  | Not Started | 0% | P5.32 |  | Synch Data Entity line 21 - Deals | Thu 3/03/22 1:10 AM | Thu 3/03/22 1:15 AM | 5 mins | Ishita Singhal | 95 | 1010-149 1310-173 | 1010 - 156 1310 - 177 | 2 min
97 |  |  | Not Started | 0% | P5.33 |  | Synch Data Entity line 22 - CPN Headers | Thu 3/03/22 1:15 AM | Thu 3/03/22 1:20 AM | 5 mins | Simaranjit Singh Bhalla | 96 | 1010-18112 1310-40880 | 1010 - 18541 1310 - 41005 | 7 mins
98 |  |  | Not Started | 0% | P5.34 |  | Synch Data Entity line 23 - CDS CPN Specifications | Thu 3/03/22 1:20 AM | Thu 3/03/22 1:40 AM | 20 mins | Ashok Singh | 97 | 1010-144896 1310-449680 | 1010 - 148328 1310 - 451055 | 36 min
99 |  |  | Not Started | 0% | P5.36 |  | Enable DW for CPN Header and Specifications, Products and All Products | Thu 3/03/22 12:50 AM | Thu 3/03/22 1:10 AM | 20 mins | Ishita Singhal | 98 |  |  | 15 min
100 |  |  | Not Started | 0% |  |  | 6.0 Master Data - Validation | Thu 3/03/22 5:10 AM | Thu 3/03/22 10:20 AM | 5.17 hrs |  |  |  |  | 2 hrs
101 |  |  | Not Started | 0% | P5.35 |  | Advise program data sync for Master Data to CE is complete | Thu 3/03/22 10:10 AM | Thu 3/03/22 10:20 AM | 10 mins | Adam Cheeseman | 98104 |  |  | 1 hr
102 |  |  | Not Started | 0% | P6.1 |  | Portal Master Data validation | Thu 3/03/22 5:10 AM | Thu 3/03/22 7:10 AM | 2 hrs | Craig James | 99FS+4 hrs |  |  | 1.5 hrs
103 |  |  | Not Started | 0% | P6.3 | Confirm that DW is active and working correctly - Amend Customer, Address, Contact, Account Team from D365 and check that changes have gone through to Portal; Then change back again. | Portal Master Data PVT | Thu 3/03/22 7:10 AM | Thu 3/03/22 10:10 AM | 3 hrs | Craig James | 101
104 |  |  | Not Started | 0% | P7.6 | cannot start before P5-23 is complete | Data Load: Customer technical data sheets manually uploaded to CE | Thu 3/03/22 7:10 AM | Thu 3/03/22 8:10 AM | 1 hr | Ross Mireylees | 101 |  |  | 2.15 hrs
105 |  |  | Not Started | 0% | P7.7 |  | Data Load: Upload Price lists to sharepoint Pricelist pdfs that will be automatically moved to CE | Thu 3/03/22 8:10 AM | Thu 3/03/22 9:10 AM | 1 hr | Mike Zur | 102 | 118 |  | 5 mins
106 |  |  | Not Started | 0% | P7.8 |  | Data Load: Upload Price lists manually to CE Pricelist pdfs that will not work with the automated job are to uploaded to CE | Thu 3/03/22 9:10 AM | Thu 3/03/22 10:10 AM | 1 hr | Ross Mireylees | 103 |  |  | 3 hrs
107 |  |  | Not Started | 0% |  |  | 7.0 Prep for Transactional Data Migration | Thu 3/03/22 5:00 PM | Sun 6/03/22 11:05 PM | 78.08 hrs
108 |  |  | Not Started | 0% | P7.1 |  | Send list of active users to Fujitsu and to remove access to Sales Order create, Order Integrator and Surplus Stock for indicated users. | Thu 3/03/22 5:00 PM | Thu 3/03/22 5:30 PM | 0.5 hrs | Craig James
109 |  |  | Not Started | 0% | P7.2 |  | Remove access to Sales Order create and Order Integrator and Surplus Stock for indicated users | Thu 3/03/22 5:30 PM | Thu 3/03/22 7:30 PM | 2 hrs | Prathima Movva | 108
110 |  |  | Not Started | 0% | P7.3 |  | Notify Fujitsu to change over integration once final invoice run is complete | Thu 3/03/22 7:30 PM | Thu 3/03/22 7:40 PM | 10 mins | Peter McIlquham | 109
111 |  |  | Not Started | 0% | P7.4 |  | Change over integration from Legacy to D365 (only after last invoice run is complete) | Thu 3/03/22 7:40 PM | Thu 3/03/22 8:40 PM | 1 hr | Andy Hunter | 110
112 |  |  | Not Started | 0% | P7.5 |  | Transactional data migration into D365 | Thu 3/03/22 8:00 PM | Sun 6/03/22 10:00 AM | 62 hrs
113 |  |  | Not Started | 0% | P7.9 |  | Stage Gate 6 - Commence Core PVT | Sun 6/03/22 10:00 AM | Sun 6/03/22 11:00 PM | 13 hrs |  | 112
114 |  |  | Not Started | 0% | P7.10 |  | Communicate NO changes to Sales Orders, Shipments, Invoices & Transfer Orders (after Stage Gate 7) | Sun 6/03/22 11:00 PM | Sun 6/03/22 11:05 PM | 5 mins | Adam Cheeseman | 113 |  |  |  | Sun 16/01/22 10:00 PM | Mon 17/01/22 3:00 AM | 4.47 hrs
115 |  |  | Not Started | 0% |  |  | 8.0 CE Transactional Data Synch | Sun 6/03/22 11:05 PM | Mon 7/03/22 3:45 AM | 4.67 hrs |  | 114 |  |  |  | Sun 16/01/22 10:00 PM | Sun 16/01/22 10:30 PM | 30 mins
116 |  |  | Not Started | 0% | P8.1 | Issue 8-1 | Prepare the SSIS files - extract Sales Order headers and lines, Extract Invoice headers and lines and prepare for CE developer | Sun 6/03/22 11:05 PM | Sun 6/03/22 11:35 PM | 30 mins | Ishita Singhal | 114 |  |  | 22 min | Sun 16/01/22 10:30 PM | Sun 16/01/22 10:35 PM | 5 mins
117 |  |  | Not Started | 0% | P8.2 | Issue P8-2 and P8-3 together | Synch Data Entity line 25 - CDS sales order headers | Sun 6/03/22 11:35 PM | Sun 6/03/22 11:40 PM | 5 mins | Ashok Singh,Simaranjit Singh Bhalla | 116 | 1010 - 3404 1310 - 6551 | 1010 - 3497 1310 - 6569 | 13 min | Sun 16/01/22 10:35 PM | Sun 16/01/22 11:10 PM | 35 mins
118 |  |  | Not Started | 0% | P8.2.5 | NEW 01/02/22 | Disable Plugin PreSalesOrderDetailsCreateUpdate on Order Line Item and publish customizations | Sun 6/03/22 11:40 PM | Sun 6/03/22 11:45 PM | 5 mins | Ashok Singh,Simaranjit Singh Bhalla | 117 |  |  | new | Sun 16/01/22 11:10 PM | Sun 16/01/22 11:12 PM | 2 mins
119 |  |  | Not Started | 0% | P8.3 |  | Synch Data Entity line 26 - CDS sales order lines | Sun 6/03/22 11:45 PM | Mon 7/03/22 12:20 AM | 35 mins | Ashok Singh,Simaranjit Singh Bhalla | 118 | 1010 - 11638 1310 - 13893 | 1010 - 10846 1310 - 13265 | 37 min | Sun 16/01/22 11:12 PM | Sun 16/01/22 11:13 PM | 1 min
120 |  |  | Not Started | 0% | P8.3.5 | NEW 01/02/22 | Enable Plugin PreSalesOrderDetailsCreateUpdate on Order Line Item and publish customizations | Mon 7/03/22 12:20 AM | Mon 7/03/22 12:25 AM | 5 mins | Ashok Singh,Simaranjit Singh Bhalla | 119 |  |  | new | Sun 16/01/22 11:13 PM | Sun 16/01/22 11:58 PM | 40 mins
121 |  |  | Not Started | 0% | P8.4 | Issue P8-4, 8-5, 8-6, 8-7 at the same time to Ishita | Synch Data Entity line 27a - Outbound shipment headers | Mon 7/03/22 12:25 AM | Mon 7/03/22 12:30 AM | 5 mins | Ishita Singhal | 120 | 1010 - 11 1310 - 9 | 1010 - 0 1310 - 19 | 1 min | Sun 16/01/22 12:00 AM | Sun 16/01/22 12:50 AM | 50 mins
122 |  |  | Not Started | 0% | P8.5 |  | Synch Data Entity line 27b - CDS Transfer order shipment header | Mon 7/03/22 12:30 AM | Mon 7/03/22 1:10 AM | 40 mins | Ishita Singhal | 121 | 1010 - 125 1310 - 5022 | 1010 - 252 1310 - 4901 | 23 min | Sun 16/01/22 12:50 AM | Sun 16/01/22 12:55 AM | 5 mins
123 |  |  | Not Started | 0% | P8.6 |  | Synch Data Entity line 28a - CDS Outbound shipment load lines | Mon 7/03/22 1:10 AM | Mon 7/03/22 1:15 AM | 5 mins | Ishita Singhal | 122 | 1010 - 19 1310 - 16 | 1010 - 0 1310 - 67 | 4 min | Sun 16/01/22 12:55 AM | Sun 16/01/22 1:30 AM | 35 mins
124 |  |  | Not Started | 0% | P8.7 |  | Synch Data Entity line 28b - CDS Transfer order shipment line | Mon 7/03/22 1:15 AM | Mon 7/03/22 2:05 AM | 50 mins | Ishita Singhal | 123 | 1010 - 0 1310 - 7634 | 1010 - 0 1310 - 7438 | 38 min | Sun 16/01/22 1:30 AM | Sun 16/01/22 1:35 AM | 2 mins
125 |  |  | Not Started | 0% | P8.8 | Invoices must follow shipments otherwise invoices will miss critical data added a critical predecessor of invoices | Synch Data Entity line 29 - Sales invoice headers V2 | Mon 7/03/22 2:05 AM | Mon 7/03/22 2:10 AM | 5 mins | Simaranjit Singh Bhalla | 124 | 1010 - 22384 1310 - 65543 | 1010 - 6865 1030 - 15885 | 10 min | Sun 16/01/22 1:35 AM | Sun 16/01/22 1:45 AM | 10 mins
126 |  |  | Not Started | 0% | P8.9 |  | Synch Data Entity line 30 - Sales invoice lines V2 | Mon 7/03/22 2:10 AM | Mon 7/03/22 2:45 AM | 35 mins | Simaranjit Singh Bhalla | 125 | 1010 - 22386 1310 - 65511 | 1010 - 6865 1310 - 15895 | 58 min | Sun 16/01/22 1:45 AM | Sun 16/01/22 1:47 AM | 2 mins
127 |  |  | Not Started | 0% | P8.10 | Issue P8-10 to P8-14 | Synch Data Entity line 31 - CDS sales quotation lines | Mon 7/03/22 2:05 AM | Mon 7/03/22 2:10 AM | 5 mins | Ishita Singhal | 124 | 1010 - 0 1310 - 0 | 1010 - 0 1310 - 0 | 2 min | Sun 16/01/22 1:47 AM | Sun 16/01/22 1:50 AM | 1 min
128 |  |  | Not Started | 0% | P8.11 |  | Synch Data Entity line 32 - Return order headers | Mon 7/03/22 2:10 AM | Mon 7/03/22 2:20 AM | 10 mins | Ishita Singhal | 127 | 1010 - 0 1310 - 0 | 1010 - 0 1310 - 0 | 1 min | Sun 16/01/22 1:50 AM | Mon 17/01/22 2:20 AM | 30 mins
129 |  |  | Not Started | 0% | P8.12 |  | Synch Data Entity line 33 - CDS Return order lines | Mon 7/03/22 2:20 AM | Mon 7/03/22 2:25 AM | 5 mins | Ishita Singhal | 128 | 1010 - 0 1310 - 0 | 1010 - 0 1310 - 0 | 1 min | Mon 17/01/22 2:20 AM | Mon 17/01/22 2:50 AM | 0.5 hrs
130 |  |  | Not Started | 0% | P8.13 |  | Synch Data Entity line 34 - CDS sales line attachments | Mon 7/03/22 2:25 AM | Mon 7/03/22 2:30 AM | 5 mins | Ishita Singhal | 129 | 1010 - 0 1310 - 0 | 1010 - 0 1310 - 0 | 3 min | Mon 17/01/22 2:50 AM | Mon 17/01/22 3:20 AM | 30 mins
131 |  |  | Not Started | 0% | P8.14 |  | Synch Data Entity line 35 - CDS Transfer order lines | Mon 7/03/22 2:30 AM | Mon 7/03/22 3:00 AM | 30 mins | Ishita Singhal | 130 | 1010 - 0 1310 - 8325 | 1010 - 0 1310 - 8028 | 42 min | Mon 17/01/22 2:20 AM | Mon 17/01/22 6:40 AM | 4.17 hrs
132 |  |  | Not Started | 0% | P8.15 | Issue P8-15 and P8-16 time reduced to 15mins after FDR2 | DW switch on for Sales Orders, Shipments, Invoices & Transfer Orders | Mon 7/03/22 3:00 AM | Mon 7/03/22 3:15 AM | 15 mins | Ishita Singhal | 131 |  |  | 5 min | Mon 17/01/22 2:20 AM | Mon 17/01/22 4:20 AM | 2 hrs
133 |  |  | Not Started | 0% | P8.16 |  | Ensure Power Automates are all active | Mon 7/03/22 3:15 AM | Mon 7/03/22 3:45 AM | 30 mins | Ashok Singh | 132 |  |  | 10 min | Mon 17/01/22 12:13 AM | Mon 17/01/22 2:13 AM | 2 hrs
134 |  |  | Not Started | 0% |  |  | 9.0 Transaction Data validation | Mon 7/03/22 2:30 AM | Mon 7/03/22 5:10 AM | 2.67 hrs | [5 empty] | Mon 17/01/22 2:13 AM | Mon 17/01/22 2:23 AM | 10 mins
135 |  |  | Not Started | 0% | P9.1 | Issue at same time as P8-15. This task must finish by 8am when backlog despatch processing commences. Ishita, Sim and Ashok to stay online or oncall to provide assistance if issue found in validation | Portal Transactional Data validation | Mon 7/03/22 3:00 AM | Mon 7/03/22 5:00 AM | 2 hrs | Craig James | 131 |  |  | 5 hrs | Mon 17/01/22 2:23 AM | Mon 17/01/22 4:23 AM | 2 hrs
136 |  |  | Not Started | 0% | P9.3 | this could be delegated to CJ | Advise program data sync for Transactional Data to CE is complete | Mon 7/03/22 5:00 AM | Mon 7/03/22 5:10 AM | 10 mins | Adam Cheeseman,Craig James | 135 |  |  | 5 min | Mon 17/01/22 2:23 AM | Mon 17/01/22 6:33 AM | 4.17 hrs
137 |  |  | Not Started | 0% | P9.4 | This task is not issued as part of Portal runsheet. Belongs to Core PVT runsheet. Confirm with Darren B if this has any predecessors. Add task to BP runsheet to identify sales orders to load as part of this PVT | Core PVT: Create Sales Orders from Portal | Mon 7/03/22 2:30 AM | Mon 7/03/22 4:30 AM | 2 hrs | Craig James | 64 |  |  |  | Mon 17/01/22 2:23 AM | Mon 17/01/22 2:33 AM | 10 mins
138 |  |  | Not Started | 0% |  |  | 10.0 Start-up | Mon 7/03/22 5:10 AM | Mon 7/03/22 7:20 AM | 2.17 hrs | [5 empty] | Mon 17/01/22 2:33 AM | Mon 17/01/22 4:33 AM | 2 hrs
139 |  |  | Not Started | 0% | P10.1 |  | Stage Gate 8 - Begin Processing Backlog | Mon 7/03/22 5:10 AM | Mon 7/03/22 5:20 AM | 10 mins | Master runsheet coordinator | 136
140 |  |  | Not Started | 0% | P10.3 |  | Observe records in Portal for Shipments, Invoices, Sales Orders created as part of Start up PVT | Mon 7/03/22 5:20 AM | Mon 7/03/22 7:20 AM | 2 hrs | Craig James | 139
141 |  |  | Not Started | 0% | P10.5 |  | Activate Portal User and send welcome emails | Mon 7/03/22 5:40 AM | Mon 7/03/22 6:40 AM | 1 hr | Ashok Singh | 64